## How to use
How to use this template
Event Planner ¦ Free template from simplifylearn.com
Quick start
1. On the Tasks sheet, enter the event name, date, venue, budget and expected guests in the yellow cells.
2. Task due dates calculate automatically from "Weeks before event". Change the weeks to suit your timeline.
3. Set each task's Status. Overdue tasks turn red and finished tasks turn green.
4. Track costs on the Budget sheet: estimated vs actual, and what is still unpaid.
5. Manage invitations on the Guests sheet. RSVP counts update automatically.
Good to know
• Start planning 8–12 weeks ahead for most business events, and longer for large conferences.
• Keep 10% of the budget as contingency for surprises.
• Send a reminder to guests 2–3 days before the event.
• Amounts use 3 decimals for Bahraini dinar.
Yellow cells = your input. White cells with formulas calculate automatically.
Works in Excel and Google Sheets (File > Import > Upload). More free templates: simplifylearn.com

## Tasks
Event Planner
Free template from simplifylearn.com
Event: | Annual Customer Evening |  |  | Budget (BHD): | 3500 | Tasks done:
Event date: | 2026-12-17 |  |  | Expected guests: | 120 | Overdue:
Venue: | Hotel ballroom, Manama |  |  | Days to go:
Task | Category | Owner | Weeks before event | Due date | Status | Done on | Notes
Agree goals, date and budget | Planning | Manager | 12 |  | Done
Book the venue | Venue | Admin | 10 |  | Done
Create guest list | Guests | Sales | 9 |  | Done
Book catering and confirm menu | Catering | Admin | 8 |  | In progress
Send save-the-date | Guests | Marketing | 8 |  | In progress
Book AV, sound and stage | Venue | Admin | 6 |  | Not started
Design invitations and banners | Marketing | Marketing | 6 |  | Not started
Send invitations | Guests | Marketing | 5 |  | Not started
Order gifts / giveaways | Logistics | Admin | 4 |  | Not started
Prepare agenda and speakers | Program | Manager | 4 |  | Not started
Follow up RSVPs | Guests | Sales | 2 |  | Not started
Confirm final numbers with venue | Venue | Admin | 1 |  | Not started
Print name badges and signs | Logistics | Admin | 1 |  | Not started
Send reminder to guests | Guests | Marketing | 0.5 |  | Not started
Thank-you message and photos | Follow-up | Marketing | -1 |  | Not started

## Budget
Event Budget
Free template from simplifylearn.com
Budget: |  | Actual spent: |  | Remaining:
Still to pay:
Item | Category | Estimated (BHD) | Actual (BHD) | Difference | Paid? | Supplier / notes
Venue hire | Venue | 800 | 800 |  | Yes
Catering (120 guests) | Catering | 1800 | 0 |  | No
AV and sound | Venue | 350 | 0 |  | No
Invitations and printing | Marketing | 120 | 95 |  | Yes
Gifts | Logistics | 250 | 0 |  | No
Photographer | Marketing | 150 | 0 |  | No
Contingency (10%) | Planning | 350 | 0 |  | No
Total

## Guests
Guest List and RSVPs
Free template from simplifylearn.com
Attending: |  | Pending: |  | Declined:
Name | Company | Mobile | Email | Invited on | RSVP | People | Notes (diet, access)
Khalid Ahmed | ABC Trading |  |  | 2026-11-12 | Yes | 2
Layla Mohammed | Gulf Foods |  |  | 2026-11-12 | Pending | 1
Ali Hasan | Bahrain Logistics |  |  | 2026-11-12 | No | 1
Huda Jassim | Star Clinics |  |  | 2026-11-12 | Yes | 1

## Lists
Categories | Status
Planning | Not started
Venue | In progress
Catering | Done
Guests | Cancelled
Marketing
Program
Logistics
Follow-up
Edit or add items in the yellow cells. Drop-downs use rows 2–15 of each column.