## Meeting Minutes
Meeting Minutes
Fill in the yellow cells. Copy this sheet for each meeting and add the actions to the Action Log.
Meeting: |  | Monthly team meeting
Date: |  | 2026-10-18 21:00
Time: |  | 10:00 – 11:00
Location: |  | Meeting room 2 / Teams
Chair: |  | Sara Ali
Minutes by: |  | Omar Khalid
ATTENDEES
# | Name | Role | Present?
1 | Sara Ali | Manager | Yes
2 | Omar Khalid | Sales | Yes
3 | Noor Hassan | Finance | Yes
4 | Ali Ahmed | Operations | Apologies
5
6
7
8
AGENDA, DISCUSSION AND DECISIONS
# | Agenda item and discussion | Decision | Presenter
1 | Review of last month's sales: sales were 8% above target; online orders grew fastest. | Keep the weekend offer for one more month. | Omar
2 | New leave request process: managers will approve leave in the shared tracker from next month. | Approved. HR to send instructions. | Sara
3 | Q4 budget: printing and marketing costs are higher than planned. | Noor to suggest savings by the next meeting. | Noor
4
5
6
ACTION ITEMS
# | Action | Owner | Due date | Status
1 | Extend weekend offer and update social media posts | Omar | 2026-10-25 21:00 | Open
2 | Send leave process instructions to all staff | Sara | 2026-10-21 21:00 | Open
3 | Prepare cost-saving options for printing and marketing | Noor | 2026-11-01 21:00 | Open
4 | Share last month's sales report | Omar | 2026-10-16 21:00 | Done
5
6
7
8
9
10
Next meeting: |  | 2026-11-17 21:00
| Approved by (chair): ____________________ |  | Date: __________

## Action Log
Action log
Keep every action from every meeting in one list. Overdue actions turn red.
Open actions:
Meeting date | Meeting | Action | Owner | Due date | Status | Notes
2026-10-18 21:00 | Monthly team meeting | Extend weekend offer and update social media posts | Omar | 2026-10-25 21:00 | Open
2026-10-18 21:00 | Monthly team meeting | Send leave process instructions to all staff | Sara | 2026-10-21 21:00 | Open
2026-10-18 21:00 | Monthly team meeting | Prepare cost-saving options for printing and marketing | Noor | 2026-11-01 21:00 | Open
2026-10-18 21:00 | Monthly team meeting | Share last month's sales report | Omar | 2026-10-16 21:00 | Done

## How to use
How to use this template
Free template from simplifylearn.com
Quick start
1. Before the meeting: fill in the meeting details, attendees and agenda items on the Meeting Minutes sheet.
2. During the meeting: write a short summary of each discussion and the decision made. Keep it brief — decisions and actions matter most.
3. Add every action with ONE owner and a due date. Overdue open actions turn red.
4. After the meeting: copy the action items into the Action Log so you can follow up across meetings, then save as PDF and share.
5. For the next meeting, copy the Meeting Minutes sheet (right-click the tab → Move or Copy → Create a copy) and start by reviewing open actions.
Tip: AI can turn rough notes into minutes. Paste your notes and ask: "Turn these into minutes with decisions and an action table (Action ¦ Owner ¦ Due date)."
Works in Excel 2016 or later, Excel for the web and Google Sheets (File → Import).